**Tentative Timeline for 21st CCLC Grants RFP**

|  |  |
| --- | --- |
| **May – November 2017** | ODE meets with 21st CCLC Advisory Group to get input for the Continuous Quality Improvement Processes (CQIP) Logic Model Tool being developed by American Institute for Research (AIR).  |
| **November 16th 2017** | AIR will present at the 21st CCLC conference; the process that was developed for the CQIP. |
| **December 2017** | 21st CCLC – Title IV-B Grant Application Request for Proposal (RFP) is finalized. |
| **January– February 2018** | RFP Technical Assistance for Applicants: Regional and Statewide Training and Support. (Webinar or Go-to-Meeting) |
| **February 2018** | ODE 21st CCLC RFP disseminated  |
| **March - April 2018** | Review teams are recruited, selected and trained for the RFP review. |
| **April 9, 2018** | RFP due to the Oregon Department of Education by 5:00 PM. |
| **May 7, 2018** | 21st CCLC Grant Recipient Awards are announced |
| **June 2018** | Grantee orientation: Training and Technical Assistance for new grantees. (TBD) |
| **July 1, 2018** | 21st CCLC Program Year begins |